Phase 1 (first 2 weeks)

- Understand Bob thoroughly (have shared Seismic and other links).

- Download the free trial and use it - write some real code, Spend at least 3-5 hours using it. Put in some real code and test. Understand what it is good at/not good at.

- Apply for a full subscription (link shared)

- Do a comparative analysis of Bob v/s other competitors (should be comprehensive to tackle questions later). Have a clear view to 3 things that Bob does really very well and 3 limitations.

- Undertake learnings on "Your Learning" - Sales Foundation, etc

- Identify developer communities and map out the kinds of conversations and the personas and analytics around how many members, how many discussion forums, SMEs/influencers and their followers (some common ones: GitHub, Stak Overflow, Reddit, Hacker News, Discord, LinkedIn, Dev.to/Hashnode)

- Read the last 1 month's discussions on each platform - what are the recurring themes, pain points, tone used

- Identify about 5 discussion areas that you could begin participating in Phase 2

- Segment conversations into distinct focus areas and stakeholder personas based on initial research findings.

- Surface any "IBM SMEs" engaging in conversations

- Map out everything that is needed to engage meaningfully with developers, SMEs/Influencers

Phase 2 (Weeks 3-6)

- Introduction to Product Management(PM), Product Marketing (PMM), Developer Relations.

- Map out all 'shareable' assets available such as use cases, tutorials, 'honest comparisons', push to trial assets, etc.

- Create a "how to respond when ..." guide

- Week 4 - First 2 community posts (across 2-3 platforms),

- Week 4 - first 3-5 forum responses posted,

- Week 5 - 1 influencer contacted on atleast 3 platforms

- Have a structured way to capture feedback and 'close the loop'. Atleast 3-4 feedback points shared with PM/PMM

- Week 6 - Assessment of increase in Trials and tracking to community activity.

Phase 3 (needs to be fleshed out at a later stage)

- Identify Startup Communities and build out a plan to engage with these communities.

- Run AMA sessions